## Dashboard
Task ID | Task Name | Team | Task Owner | Start Date | Due Date | Task Duration | Status | Overdue? | Comments | Priority
T001 | Prepare Q4 Financial Report | Finance | Sarah Johnson | 2026-02-02 | 2026-02-20 | 18 | Completed | FALSE | Submitted to CFO for review. | High
T002 | Conduct Market Research | Strategy | Sarah Johnson | 2026-02-03 | 2026-02-23 | 20 | Completed | FALSE | Draft findings ready; awaiting survey data. | Medium
T003 | Redesign Website Homepage | Strategy | David Kim | 2026-02-07 | 2026-02-28 | 21 | In Progress | TRUE | Wireframes approved; development in progress. | Low
T004 | Update Sales Forecast for FY2026 | Finance | Sarah Johnson | 2026-02-12 | 2026-02-28 | 16 | Completed | FALSE | Final version shared with Sales Director. | Low
T005 | Implement CRM Upgrade | Strategy | James Miller | 2026-02-18 | 2026-02-28 | 10 | In Progress | TRUE | Vendor confirmed delivery timeline. | Low
T006 | Plan Annual Company Retreat | HR | David Kim | 2026-02-20 | 2026-02-25 | 5 | In Progress | TRUE | Venue options being shortlisted. | Low
T007 | Review Legal for Contracts | HR | Alex Chen | 2026-02-23 | 2026-02-26 | 3 | Not Started | TRUE | Updated contracts aligned with new regulation. | Medium
T008 | Launch Social Media Campaign | Marketing | Alex Chen | 2026-02-23 | 2026-02-28 | 5 | In Progress | TRUE | Initial creatives approved, campaign scheduled. | High
T009 | Recruit New Data Analyst | HR | Sarah Johnson | 2026-03-02 | 2026-03-14 | 12 | Completed | FALSE | First round of interviews completed. | Medium
T010 | Conduct Employee Survey | HR | Sarah Johnson | 2026-03-05 | 2026-03-10 | 5 | In Progress | TRUE | Survey questions finalized. | Low
T011 | Prepare Investor Presentation | Finance | David Kim | 2026-03-07 | 2026-03-18 | 11 | Completed | FALSE | Draft slides ready; awaiting financial highlights. | High
T012 | Upgrade Infrastructure | Strategy | Sarah Johnson | 2026-03-11 | 2026-03-20 | 9 | Completed | FALSE | External consultant engagement pending. | Medium
T013 | Evaluate Vendor Proposals for Logistics | Strategy | Emily Davis | 2026-03-13 | 2026-03-24 | 11 | In Progress | FALSE | Three proposals shortlisted for management review. | High
T014 | Draft Q1 Marketing Strategy | Strategy | Emily Davis | 2026-03-15 | 2026-03-29 | 14 | In Progress | FALSE | Kick-off meeting scheduled next week. | High
T015 | Audit Internal Expense Reports | Finance | Emily Davis | 2026-03-16 | 2026-03-30 | 14 | Not Started | FALSE | Waiting for submission of all departmental reports. | High
Formulas:
Overdue? = AND([Status]<>"Completed",[Due Date]<TODAY())
Overdue? = AND([Status]<>"Completed",[Due Date] < TODAY())
TASK TRACKER
6
Completed
Total Tasks
13.03.2026
Due Today
0
7
Overdue
6
Not Started
2
In Progress
TODAY'S DATE
15

## Support Sheet
Status | Count | Owners | Count | Team | Count | Overdue | Priority | Count | Due Today | Date Today
Completed | 6 | Sarah Johnson | 6 | Finance | 4 | 6 | High | 6 | 0 | 2026-03-13
In Progress | 7 | David Kim | 3 | Strategy | 6 |  | Medium | 4
Not Started | 2 | James Miller | 1 | HR | 4 |  | Low | 5
Total | 15 | Alex Chen | 2 | Marketing | 1 |  | Total
|  | Emily Davis | 3